## Overview (hidden)
Project Costing Breakdown
Generated on | December 10, 2024
Generated for | Grand Erie District School Board
Generated by | Frank Mesicek
Facilities | - All -
Funding | School Condition Improvement (SCI) Restricted, School Condition Improvement (SCI) Unrestricted, School Renewal Allocation (SRA)
Funding Year | 2024-2025, 2023-2024
Project Type | - All -
Statuses | - All -
Stages | - All -
Managers | - All -
Initiatives | - All -
Project # | - None -

## Data
School Name | Project Type | Project Description | Start Date | Completion Date or Anticipated Date for Completion | Percent Complete
Agnes G. Hodge | Site Work | Beautification 24/25 | 2024-11-25 | 2025-08-29 | 1%
Agnes G. Hodge | Renovations - Learning Commons | Learning Commons | 2024-01-05 | 2024-08-31 | 100%
Bellview PS | Paving | Playground Asphalt Pavement Retrofit | 2024-03-08 | 2024-08-26 | 100%
Bellview PS | Renovation/Upgrade | Beautification 24/25 | 2024-11-25 | 2025-08-29 | 1%
Bloomsburg PS | HVAC | Boiler Replacement | 2023-12-21 | 2024-12-31 | 95%
Bloomsburg PS | Renovation/Upgrade | Beautification 24/25 | 2024-11-25 | 2025-08-29 | 1%
Boston PS | Renovation/Upgrade | Beautification 24/25 | 2024-11-25 | 2025-08-29 | 1%
Branlyn PS | Windows and Doors | Window and Door Replacements | 2024-02-16 | 2024-11-13 | 100%
Brantford Collegiate &VS | Paving | Parking Lot Asphalt Pavement Retrofit | 2024-03-08 | 2024-08-26 | 100%
Brantford Collegiate &VS | Renovation/Upgrade | Hospitality Classroom Renovation | 2024-03-26 | 2024-12-30 | 99%
Brantford Collegiate &VS | Site Work | Storm Sewer Addition | 2024-11-01 | 2024-11-29 | 100%
Brier Park PS | Renovation/Upgrade | HVAC Upgrade/Open Concept Conversion Phase 2 | 2024-02-27 | 2024-09-14 | 100%
Burford Elementary | Site Work | Septic System Upgrade | 2023-05-04 | 2024-09-16 | 100%
Burford Elementary | Windows and Doors | Entrance Door Replacement | 2024-02-16 | 2025-03-15 | 90%
Burford Elementary | Renovation/Upgrade | Beautification 24/25 | 2024-11-25 | 2025-08-29 | 1%
Caledonia Centennial PS | Masonry | Masonry Cladding Installation - Gym Area | 2024-06-10 | 2024-12-06 | 100%
Cayuga Secondary School | Roofing | Roof Replacement Areas 203 and 207 | 2023-11-02 | 2024-06-30 | 100%
Cayuga Secondary School | Electrical | Electrical Panel Upgrades | 2024-01-22 | 2024-10-01 | 100%
Cayuga Secondary School | Electrical | Electrical Panel Upgrades Phase 2 | 2024-11-22 | 2025-08-29 | 1%
Cedarland PS | Paving | Tennis Court Replacement | 2024-03-01 | 2024-12-10 | 100%
Cedarland PS | Renovations - Learning Commons | Learning Commons | 2024-11-01 | 2025-03-30 | 1%
Central-Brantford | Windows and Doors | Playground Door Replacements | 2024-02-16 | 2024-11-05 | 100%
Central-Brantford | HVAC | NERVA REME Installations/Duct Seal | 2024-03-25 | 2024-11-26 | 100%
Courtland PS | HVAC | Boiler Replacement | 2023-12-21 | 2025-01-31 | 95%
Delhi District Secondary | HVAC | Unit Ventilator Replacement | 2024-01-22 | 2025-04-26 | 65%
Delhi District Secondary | Renovation/Upgrade | Machine Shop Renovations | 2024-07-16 | 2024-12-30 | 99%
Delhi District Secondary | Electrical | Electrical Service Upgrade | 2024-11-22 | 2025-08-29 | 1%
Delhi PS | Electrical | Electrical Service Upgrade | 2024-01-22 | 2025-08-29 | 1%
Dufferin PS | Renovations - Learning Commons | Learning Commons | 2023-12-15 | 2024-10-10 | 100%
Dunnville Secondary School | HVAC | Boiler Replacement | 2023-12-21 | 2024-12-20 | 98%
Dunnville Secondary School | Electrical | Electrical Panel Upgrades | 2024-01-22 | 2024-10-01 | 100%
Dunnville Secondary School | HVAC | NERVA REME Installations/Duct Seal | 2024-03-25 | 2024-11-27 | 100%
Dunnville Secondary School | Renovation/Upgrade | Small Gym Washroom Addition | 2024-03-27 | 2024-10-11 | 100%
Dunnville Secondary School | Electrical | Electrical Panel Upgrades Phase 2 | 2024-11-22 | 2025-08-29 | 1%
Echo Place | Paving | Asphalt Replacement | 2024-01-29 | 2024-09-15 | 100%
Echo Place | Renovation/Upgrade | Beautification 24/25 | 2024-11-25 | 2025-08-29 | 1%
Edith Monture Elementary School | Paving | Pavement Rehabilitation/Site Improvement | 2024-03-08 | 2024-11-18 | 100%
Elgin Avenue PS | Renovation/Upgrade | Renovation | 2023-11-30 | 2024-09-30 | 100%
GELA-Rawdon | Roofing | Roof Replacement Areas C2-C5 | 2023-11-02 | 2024-08-30 | 100%
GELA-Rawdon | Renovations - Learning Commons | Learning Commons | 2023-12-15 | 2024-04-15 | 100%
GELA-Rawdon | Windows and Doors | Window and Door Replacements | 2024-11-22 | 2025-08-29 | 1%
Glen Morris Central PS | Renovations - Learning Commons | Learning Commons | 2024-10-01 | 2025-08-29 | 1%
Grandview (Brantford) | HVAC | NERVA REME Installations/Duct Seal | 2024-03-25 | 2024-11-28 | 100%
Greenbrier PS | Roofing | Roof Replacement Area 201 | 2023-11-02 | 2024-08-30 | 100%
Hagersville Secondary School | HVAC | Boiler Replacement | 2023-12-21 | 2025-01-15 | 95%
Hagersville Secondary School | Electrical | Electrical Panel Upgrades | 2024-01-22 | 2024-10-01 | 100%
Hagersville Secondary School | Other | Transit Countertop Replacement | 2024-06-10 | 2024-11-30 | 100%
Hagersville Secondary School | Masonry | Chimney Removal | 2024-10-01 | 2025-08-29 | 1%
Hagersville Secondary School | Electrical | Electrical Panel Upgrades Phase 2 | 2024-11-22 | 2025-08-29 | 1%
Houghton PS | Renovation/Upgrade | Interior Renovation/Modernization | 2023-11-27 | 2025-05-30 | 50%
Houghton PS | HVAC | Boiler Replacement | 2023-12-15 | 2024-12-31 | 98%
J.L. Mitchener PS | Roofing | Roofing Replacement Area 105 | 2023-11-02 | 2024-08-30 | 100%
J.L. Mitchener PS | Roofing | Roofing Replacement - Section 105 | 2024-11-01 | 2025-08-29 | 1%
James Hillier PS | Electrical | Electrical Upgrades | 2024-01-18 | 2024-08-30 | 100%
James Hillier PS | HVAC | Boiler Replacement | 2024-11-25 | 2025-08-29 | 1%
Jarvis PS | Roofing | Roof Replacement Areas 101, 102, 103, 202 | 2023-11-02 | 2024-08-30 | 100%
Jarvis PS | Renovation/Upgrade | Beautification 24/25 | 2024-11-25 | 2025-08-29 | 1%
King George PS | Renovations - Learning Commons | Learning Commons | 2023-12-15 | 2024-10-08 | 100%
King George PS | Windows and Doors | Various Entry Door Replacements | 2024-01-22 | 2024-10-25 | 98%
King George PS | Masonry | Repointing - Wall Rehabilitation | 2024-02-22 | 2024-11-12 | 100%
Lansdowne-Costain | HVAC | Boiler Replacement | 2023-12-15 | 2024-12-30 | 99%
Lynndale Heights | Roofing | Roof Replacement Areas 101, 201-205, 301 | 2023-11-02 | 2025-04-30 | 98%
Major Ballachey PS | Renovation/Upgrade | Interior Renovations | 2023-11-27 | 2024-10-14 | 100%
Major Ballachey PS | Windows and Doors | PG & Gym Door Replacement | 2024-01-22 | 2024-12-20 | 100%
McKinnon Park SS | Windows and Doors | Door Replacement | 2024-01-22 | 2024-12-06 | 100%
McKinnon Park SS | HVAC | Mechanical Upgrades Phase 3 | 2024-02-01 | 2024-11-22 | 100%
McKinnon Park SS | Security | Vape Detection | 2024-07-24 | 2024-12-05 | 100%
McKinnon Park SS | HVAC | Mechanical Upgrades Phase 4 | 2024-12-02 | 2025-08-29 | 1%
Mount Pleasant PS | HVAC | Boiler Replacement | 2023-12-15 | 2024-12-30 | 99%
Mount Pleasant PS | Renovations - Learning Commons | Learning Commons | 2024-12-02 | 2025-08-29 | 1%
North Park C&VS | Renovation/Upgrade | Classroom Kitchen Renovation | 2023-11-01 | 2025-01-06 | 99%
North Park C&VS | Roofing | Roof Replacement Areas 202, 203, 214, 216, 301 | 2023-11-02 | 2024-08-30 | 100%
North Park C&VS | Electrical | Electrical Panel Upgrade | 2024-01-22 | 2024-12-31 | 98%
North Park C&VS | Windows and Doors | Second Floor Alcove Window Replacement | 2024-02-16 | 2025-04-25 | 20%
North Park C&VS | Renovation/Upgrade | Innovation Centre | 2024-09-06 | 2024-11-01 | 100%
North Park C&VS | Electrical | Electrical Panel Upgrades Phase 2 | 2024-11-22 | 2025-08-29 | 1%
North Ward PS | Paving | Pavement Rehabilitation and Site Improvement | 2024-03-08 | 2024-09-20 | 100%
Onondaga-Brant PS | Renovation/Upgrade | Hallway/Gym Renovation | 2024-03-22 | 2025-03-22 | 95%
Onondaga-Brant PS | Renovations - Learning Commons | Learning Commons | 2024-10-01 | 2025-08-29 | 1%
Paris Central PS | Renovations - Learning Commons | Learning Commons | 2024-03-25 | 2024-10-01 | 100%
Paris DHS | Renovation/Upgrade | Cafeteria Kitchen Renovation | 2023-10-19 | 2025-02-01 | 60%
Paris DHS | HVAC | Boiler Replacement | 2023-12-21 | 2024-12-30 | 95%
Paris DHS | Windows and Doors | Replacement of Entrance Doors | 2024-02-16 | 2024-11-09 | 100%
Paris DHS | Roofing | Roofing Replacement - Section 101, 105, 107, 108, 112, 204-206, 208 | 2024-11-01 | 2025-08-29 | 1%
Pauline Johnson C&VS | Renovation/Upgrade | ESL Classroom Move | 2023-11-09 | 2024-05-27 | 100%
Pauline Johnson C&VS | Electrical | Electrical Upgrades | 2024-01-17 | 2024-08-30 | 100%
Rainham Central PS | Roofing | Roof Replacement Area 103 | 2023-11-02 | 2024-08-30 | 100%
Rainham Central PS | Windows and Doors | Exterior Gym Door Replacement | 2024-01-22 | 2024-11-28 | 100%
River Heights | Windows and Doors | West Side Window Replacement | 2024-01-22 | 2024-12-16 | 75%
River Heights | Roofing | Roofing Replacement - Area 106 | 2024-11-01 | 2025-08-29 | 1%
Seneca Central PS | Windows and Doors | Playground Door Replacement | 2024-01-22 | 2024-12-13 | 75%
Seneca Central PS | Electrical | Electrical Service Upgrade | 2024-09-04 | 2025-08-31 | 1%
Simcoe Composite | HVAC | Boiler Replacement | 2023-12-15 | 2024-12-31 | 98%
Simcoe Composite | Renovations - Learning Commons | Learning Commons | 2024-03-25 | 2024-12-31 | 95%
Simcoe Composite | HVAC | NERVA REME Installations/Duct Seal | 2024-03-25 | 2024-11-29 | 100%
Simcoe Composite | Electrical | Branch Panel Upgrades | 2024-02-15 | 2024-12-02 | 100%
St. George-German | Renovations - Learning Commons | Learning Commons | 2024-03-08 | 2024-11-27 | 100%
St. George-German | Roofing | Roofing Replacement - Section 101, 102, 103, 105, 210, 202, 204, 205 | 2024-11-01 | 2025-08-29 | 1%
Thompson Creek | HVAC | Boiler Replacement | 2023-11-22 | 2024-11-30 | 100%
Valley Heights Secondary | Roofing | Roof Replacement Areas 103, 104, 205 | 2023-11-02 | 2024-11-30 | 100%
Various schools | Electrical | Circuit IQ Power Mapping | 2024-02-15 | 2024-11-05 | 100%
Various schools | Site Work | Geothermal Assessments | 2024-03-08 | 2024-11-16 | 100%
Various schools | HVAC | BAS Upgrades Various Schools | 2024-04-10 | 2024-12-01 | 100%
Various schools | Plumbing; Water System | New UV Systems | 2024-07-15 | 2024-12-04 | 100%
Various schools | Roofing | Siporex/Rapidex Roof Inspections | 2024-02-08 | 2024-11-04 | 100%
Walpole North | Renovation/Upgrade | Beautification 24/25 | 2024-11-25 | 2025-08-25 | 1%
Walsh PS | HVAC | Boiler Replacement | 2023-12-15 | 2024-12-31 | 98%
Walsh PS | Renovations - Learning Commons | Learning Commons | 2024-10-01 | 2025-08-29 | 1%
Walsh PS | Roofing | Roofing Replacement - All Areas | 2024-11-01 | 2025-08-29 | 1%
Waterford District High School | Renovation/Upgrade | Grade 7/8 Renovation | 2024-01-02 | 2025-02-30 | 95%
West Lynn PS | Accessibility | Accessible Washroom | 2024-11-15 | 2025-08-29 | 1%
Woodman Drive (Cainsville PS) | Renovations - Learning Commons | Learning Commons | 2023-12-15 | 2024-08-30 | 100%
Woodman Drive (Cainsville PS) | Windows and Doors | East Playground Door Replacements | 2024-02-16 | 2024-10-29 | 100%